## PMR
ZAMBOANGA SIBUGAY POLYTECHNIC INSTITUTE | [11 empty] | Procurement Monitoring Report as of July 11, 2025
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
310300100001000 | CURTAIN FOR INOVATION | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-14 | 2025-01-14 |  | 2025-01-14 | N/A | 2025-01-14 |  | 0 |  | 2025-01-17 | 2025-01-20 | 2025-01-20 | 3 |  | 2025-01-23 | 2025-01-23 | TF | 49600 | 49600 |  | 49500 | 49500 |  | 0.0020161 | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | N/A | 2025-01-23 | Completed | FALSE | FALSE
310300100001000 | OFFICE SUPPLIES, EQUIPMENT & ROOM MAINTENANCE FOR 1ST QUARTER- ADMIN | LYNDRE G. BAYOTAS | No | NP-53.5 Agency-to-Agency | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2025-02-20 | N/A |  |  | 2025-02-22 | 2025-02-22 | TF | 98000 | 98000 |  | 95125.9 | 95125.9 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-22 | Completed
310300100001000 | MATERIALS FOR CONCTRETING PF PAVEMENT IN FRONT OF TESDA INNOVATION CENTER (4.5MX 0.15MX 121M) | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-03 | 2025-03-03 |  | 2025-03-03 | N/A | 2025-03-03 |  | 0 |  | 2025-03-04 | 2025-03-07 | 2025-03-07 | 3 |  | 2025-03-28 | 2025-03-28 | TF | 621805 | 621805 |  | 600198 | 600198 |  | 0.034749 | N/A | N/A | 2025-03-28 | 2025-03-28 | 2025-03-28 | N/A | 2025-03-28 | Completed | FALSE | FALSE
310300100001000 | CLINIC MEDICINE AND SUPPLIES FOR SCHOOL AND TRAINING SERVICES | MARIE CRIS M. SOGUE | No | NP-53.5 Agency-to-Agency | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2025-02-20 | N/A |  |  | 2025-02-20 | 2025-02-20 | TF | 1112.4 | 1112.4 |  | 1112.4 | 1112.4 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-22 | Completed
-
310300100001000 | PROCUREMENT OF KNX CERTIFIED DEVICES FOR THE PROGRAM REGISTRATION OF HIGHER NC (EIM NC IV) IN DIPLOMA IN ELECTRICAL ENGINEERING TECHNOLOGY | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2024-12-27 | 2024-12-27 |  | 2024-12-27 | N/A | 2024-12-27 |  |  |  | 2024-12-27 | 2025-02-02 | 2025-02-02 |  |  | 2025-01-30 | 2025-01-30 | TF | 961161.36 | 961161.36 |  | 649728 | 649728 |  |  | N/A | N/A | 2024-12-27 | 2024-12-27 | 2024-12-27 | N/A | 2025-01-30 | Completed | FALSE | FALSE
310300100001000 | NATIONAL COMPETENCY ASESSMENT CONSUMABLES FOR MASONRY NC I (TWSP-25) IMELDA, ZSP | AMY N.MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-14 | 2025-01-14 |  | 2025-01-14 | N/A | 2025-01-14 |  | 0 |  | 2025-01-15 | 2025-01-20 | 2025-01-20 | 5 |  | 2025-02-25 | 2025-02-25 | TF | 15150 | 15150 |  | 13100 | 13100 |  | 0.13531 | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-01-14 | N/A | 2025-02-25 | Completed | FALSE | FALSE
310300100001000 | MEALS AND SNACKS FOR TRAINERS TRAINING IN TM LEVEL II, INSTITUTE ASESSMENT | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-14 | 2025-02-14 |  | 2025-02-14 | N/A | 2025-02-14 |  | 0 |  | 2025-01-27 | 2025-01-30 | 2025-01-30 | 3 |  | 2025-02-02 | 2025-02-02 | TF | 27500 | 27500 |  | 27500 | 27500 |  | 0 | N/A | N/A | 2025-02-24 | 2025-02-24 | 2025-02-24 | N/A | 2025-02-02 | Completed | FALSE | FALSE
310300100001000 | MEALS FOR VISITORS DURING INAUGURATION OF RTIC | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-09 | 2025-01-09 |  | 2025-01-09 | N/A | 2025-01-09 |  |  |  | 2025-01-09 | 2025-01-13 | 2025-01-13 |  |  | 2025-01-14 | 2025-01-14 | TF | 12000 | 12000 |  | 12000 | 12000 |  |  | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-09 | N/A | 2025-01-14 | Completed
310300100001000 | CONSUMABLES FOR NATIONAL ASESSMENT IN MOTORCYCLE/SMALL ENGINE SERVICES NC II (TWSP-25) TALUSAN, ZSP | AMY N.MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-14 | 2025-01-14 |  | 2025-01-14 | N/A | 2025-01-14 |  | 0 |  | 2025-01-15 | 2025-01-20 | 2025-01-20 | 5 |  | 2025-02-25 | 2025-02-25 | TF | 11400 | 11400 |  | 9700 | 9700 |  | 0.14912 | N/A | N/A | 2025-01-14 | 2025-01-24 | 2025-01-14 | N/A | 2025-02-25 | Completed | FALSE | FALSE
310300100001000 | MEALS AND SNACKS FOR TECHNOLOGY TRANSFER IN CNC SIMULATOR | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-14 | 2025-01-14 |  | 2025-01-14 | N/A | 2025-01-14 |  | 0 |  | 2025-01-14 | 2025-01-14 | 2025-01-15 | 1 |  | 2025-01-16 | 2025-01-16 | TF | 17500 | 17500 |  | 14500 | 14500 |  | 0.17143 | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-01-14 | N/A | 2025-01-16 | Completed | FALSE | FALSE
310300100001000 | MEALS FOR FINANCIAL WORKSHOP F.Y. 2024 | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-13 | 2025-01-13 |  | 2025-01-13 | N/A | 2025-01-13 |  | 0 |  | 2025-01-15 | 2025-01-17 | 2025-01-17 | 2 |  | 2025-01-17 | 2025-01-17 | TF | 6250 | 6250 |  | 6250 | 6250 |  | 0 | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-01-13 | N/A | 2025-01-17 | Completed | FALSE | FALSE
310300100001000 | PROCUREMENT AND INSTALLATION OF SAFETY GLASS FOR PV CONTROLLER, INVERTER, AND STORAGE BATTERY PACK PROTECTION | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-14 | 2025-02-14 |  | 2025-02-14 | N/A | 2025-02-14 |  | 0 |  | 2025-02-17 | 2025-02-20 | 2025-02-20 | 3 |  | 2025-02-25 | 2025-02-25 | TF | 4815 | 4815 |  | 4600 | 4600 |  | 0.044652 | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-02-14 | N/A | 2025-02-25 | Completed | FALSE | FALSE
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES FOR FOOD PROCESSING NC II (SHS TVL LEARNERS-34) | AMY N.MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-17 | 2025-02-17 |  | 2025-02-17 | 2025-02-17 | 2025-02-14 |  |  |  | 2025-02-18 | 2025-02-21 | 2025-02-21 |  |  | 2025-02-28 | 2025-02-28 | TF | 57004 | 57004 |  | 52995 | 52995 |  |  | N/A | N/A | 2025-02-17 | 2025-02-17 | 2025-02-17 | N/A | 2025-02-28 | Completed
310300100001000 | MATERIALS FOR EIM NC II TRAINING - 2 BATCHES | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-07 | 2025-01-07 |  | 2025-01-07 | 2025-01-07 | 2025-01-07 |  |  |  | 2025-01-08 | 2025-01-13 | 2025-01-13 |  |  | 2025-01-29 | 2025-01-29 | TF | 190250 | 190250 |  | 134080 | 134080 |  |  | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-01-07 | N/A | 2025-01-29 | Completed
310300100001000 | TOOLS AND MATERIALS FOR SCHOOL CAMPUS MAINTENANCE | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 0 | 0 |  | 2025-03-26 | 2025-03-31 | 2025-03-31 | 5 |  | 2025-04-12 | 2025-04-12 | TF | 451480 | 451480 |  | 436100 | 436100 |  | 0.034066 | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-25 | N/A | 2025-02-05 | Completed | FALSE | FALSE
310300100001000 | MEALS AND SNACKS FOR COMPLIANCE AUDIT FOR UTPRAS AND ASSESSMENT CENTER ON MARCH 25-27, 2025 | AMY N.MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-21 | 2025-02-21 |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 0 | 0 |  | 2025-02-24 | 2025-02-27 | 2025-02-27 | 3 |  | 2025-02-27 | 2025-02-27 | TF | 44900 | 44900 |  | 44644 | 44644 |  | 0.0057016 | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-02-21 | N/A | 2025-02-27 | Completed | FALSE | FALSE
310300100001000 | MEALS AND SNACKS FOR PROVINCIAL INDUSTRY FORUM | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  |  |  | 2025-03-28 | 2025-03-28 | 2025-03-28 |  |  | 2025-03-28 | 2025-03-28 | TF | 25000 | 25000 |  | 23000 | 23000 |  |  | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-25 | N/A | 2025-03-28 | Completed
310300100001000 | MEALS AND SNACKS FOR REGIONAL ICT DEVELOPMENT TECHNICAL WORKING GROUP | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-04 | 2025-03-04 |  | 2025-03-04 | 2025-03-04 | 2025-03-04 |  |  |  | 2025-03-05 | 2025-03-05 | 2025-03-05 |  |  | 2025-03-08 | 2025-03-08 | TF | 7275 | 7275 |  | 7275 | 7275 |  |  | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-03-24 | N/A | 2025-03-05 | Completed
310300100001000 | MATERIALS FOR SKILLS DEMONSTRATION TRAINING IN 3D PRINTING ON ONE STOP SHOP SERVICE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-14 | 2025-02-14 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 |  |  |  | 2025-02-20 | 2025-02-20 | 2025-02-20 |  |  | 2025-02-20 | 2025-02-20 | TF | 4750 | 4750 |  | 4740 | 4740 |  |  | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-02-14 | N/A | 2025-02-20 | Completed
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTRATION IN ONE STOP SERVICES AT CAPITOL , IPIL ZSP (HOT & COLD COFFEE) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-14 | 2025-02-14 |  | 2025-02-14 | 2002-02-14 | 2025-02-14 |  |  |  | 2025-02-17 | 2025-02-17 | 2025-02-07 |  |  | 2025-02-14 | 1938-04-30 | TF | 5900 | 5900 |  | 5892 | 5892 |  |  | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-02-14 | N/A | 2025-02-22 | Completed
310300100001000 | MEALS AND SNACKS FOR COMPLIANCE AUDIT AND ASSESSMENT CENTER ON MARCH 25-27, 2025 | AMY N.MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-21 | 2025-02-21 |  | 2025-02-21 | 2025-02-21 | 2025-02-21 |  |  |  | 2025-02-24 | 2025-02-27 | 2025-02-27 |  |  | 2025-02-27 | 2025-02-27 | TF | 44900 | 44900 |  | 44644 | 44644 |  |  | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-27 | Completed
310300100001000 | CONSUMBLES FOR TESDA OBSERVANCE OF THE 2025 NATIONAL WOMEN'S MONTH CELEBRATION AT CONCEPTION, KABASALAN, ZS ON MARCH 18, 2025, PICHI-PICHI | JENEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-13 | 2025-03-13 |  | 2025-03-13 | 2025-03-13 | 2025-03-13 |  |  |  | 2025-03-14 | 2025-03-17 | 2025-03-17 |  |  | 2025-03-18 | 2025-03-18 | TF | 1450 | 1450 |  | 1418 | 1418 |  |  | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-18 | Completed
310300100001000 | INSTALLATION OF GLASS AND WINDOW OF ZSPI INNOVATION CENTER- SECOND FLOOR | PRESCO P. CAÑETE JR. | No | NP-53.10 Lease of Real Property and Venue | N/A | N/A |  | N/A | 2025-09-24 | 2025-09-24 |  | 2025-09-24 | 2025-09-24 | 2025-09-24 |  |  |  | 2025-09-24 | 2025-09-27 | 2025-09-27 |  |  | 2025-09-30 | 2025-09-30 | TF | 907600 | 907600 |  | 897000 | 897000 |  |  | N/A | N/A | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-30 | Completed
310300100001000 | ADDITIONAL ROOM ACCOMODATION FOR DIPLOMA DURING THE INAUGURATION OF ZSPI INNOVATION CENTER | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-07 | 2025-01-07 |  | 2025-01-07 | 2025-01-07 | 2025-01-07 |  |  |  | 2025-01-07 | 2025-01-08 | 2025-01-08 |  |  | 2025-01-10 | 2025-01-10 | TF | 4000 | 4000 |  | 3600 | 3600 |  |  | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2025-07-01 | 2025-01-10 | Completed
310300100001000 | OFFICE SUPLIES AND CONSTRUCTION MATERIALS IN PREPARATION FOR RRATI- 2024-2025 | PRESCO P. CAÑETE JR. | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2025-02-09 | 2025-02-09 |  | 2025-02-09 | 2025-02-09 | 2025-02-09 |  |  |  | 2025-02-07 | 2025-02-10 | 2025-02-10 |  |  | 2025-02-11 | 2025-02-11 | TF | 2000 | 2000 |  | 1960 | 1960 |  |  | N/A | N/A | 2025-02-09 | 2025-02-09 | 2025-02-09 | 2025-02-09 | 2025-02-11 | Completed
310300100001000 | CONSUMABLES FOR TAILAROING NC II | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-06 | 2025-02-06 |  | 2025-02-06 | 2025-02-06 | 2025-02-06 |  |  |  | 2025-02-07 | 2025-02-10 | 2025-02-10 |  |  | 2025-04-29 | 2025-04-29 | TF | 36505 | 36505 |  | 29800 | 29800 |  |  | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-04-29 | Completed
310300100001000 | OFFICE SUPPLIES , EQUIPMENT, & ROOM MAINTENANCE FOR 1ST QUARTER - ADMIN USE | LYNDRE G. BAYOTAS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-10 | 2025-03-10 |  | 2025-03-10 | 2025-03-10 | 2025-03-10 | 0 | 0 |  | 2025-03-11 | 2025-03-14 | 2025-03-14 | 3 |  | 2025-04-25 | 2025-04-25 | TF | 374640 | 374640 |  | 284430 | 284430 |  | 0.24079 | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-04-25 | Completed | FALSE | FALSE
310300100001000 | [31 empty] | -
310300100001000 | [31 empty] | -
[25 empty] | Total Allotted Budget of Procurement Activities | 3983947.76 | 3983947.76 | 0 |  |  |  | 13.28%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 3454892.3 | 3454892.3 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 529055.46 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
310300100001000 | MATERIALS & TOOLS FOR ELECTRICAL REPAIR & VENTILATION FOR CCS NC II (SHOP/WORKSTATION) | LADY KRISSETTE B. ANDICOY | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 0 | 0 |  | 2025-03-26 | 2025-03-31 | 2025-03-31 | 5 |  | N/A | N/A | N/A | 14000 | 14000 |  | 12000 | 12000 |  | 0.14286 | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | N/A | Ongoing Procurement Process
310300100001000 | CONSUMABLES FOR MASONRY NC II DIPLOMA | PHILIP D. TRAYVILLA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-18 | 2025-03-18 |  | 2025-03-18 | 2025-03-18 | 2025-03-18 | 0 | 0 |  | 2025-03-19 | 2025-03-21 | 2025-03-21 | 2 |  | N/A | N/A | N/A | 48460 | 48460 |  | 37595 | 37595 |  | 22.42% | N/A | N/A | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | N/A | Ongoing Procurement Process
310300100001000 | ASSESSMENT CONSUMABLES FOR MASONRY NC I -25 AND MASONRY NC II - 25 (TWSP) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-23 | 2025-04-23 |  | 2025-04-23 | 2025-04-23 | 2025-04-23 | 0 | 0 |  | 2025-04-24 | 2025-04-28 | 2025-04-28 | 4 |  | N/A | N/A | N/A | 32480 | 32480 |  | 21140 | 21140 |  | 34.91% | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | N/A | Ongoing Procurement Process
310300100001000 | MATERIALS FOR THE REPAINT OF METAL CHAIRS | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-01-10 | 2025-01-10 |  | 2025-01-10 | 2025-01-10 | 2025-01-10 | 0 | 0 |  | 2025-01-16 | 2025-01-16 | 2025-01-16 | 0 |  | N/A | N/A | N/A | 14400 | 14400 |  | 7299 | 7299 |  | 0.49312 | N/A | N/A | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 | N/A | Ongoing Procurement Process
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES FOR DRESSMAKING NC II (SHS TVL) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-05 | 2025-03-05 |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 0 | 0 |  | 2025-03-06 | 2025-03-10 | 2025-03-10 | 4 |  | N/A | N/A | N/A | 25270 | 25270 |  | 950 | 950 |  | 0.96241 | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05 | N/A | Ongoing Procurement Process
310300100001000 | TRAINING CONSUMABLES IN COOKERY NC II | GRETCHEN J. NUBOD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-21 | 2025-03-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  |  |  | 2025-01-22 | 2025-01-27 | 2025-01-27 |  |  | N/A | N/A | N/A | 24010 | 24010 |  | 24005 | 24005 |  |  | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | N/A | Ongoing Procurement Process
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES IN BARTENDING NC II (WALK IN 30) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-04 | 2025-03-04 |  | 2025-03-04 | 2025-03-04 | 2025-03-04 |  |  |  | 2025-03-04 | 2025-03-04 | 2025-03-07 |  |  | N/A | N/A | N/A | 31814 | 31814 |  | 29910 | 29910 |  |  | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | N/A | Ongoing Procurement Process
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES FOR BREAD AND PASTRY PRODUCTION NC II (TWSP- 65 & PESFA- 20) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-28 | 2025-04-28 |  | 2025-04-28 | 2025-04-28 | 2025-04-28 |  |  |  | 2025-04-29 | 2025-05-02 | 2025-05-02 |  |  | N/A | N/A | N/A | 59040 | 59040 |  | 55200 | 55200 |  |  | N/A | N/A | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | N/A | Ongoing Procurement Process
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES FOR BREAD AND PASTRY PRODUCTION NC II (SHS TVL LEARNERS -60/AUDITOR | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-18 | 2025-02-18 |  | 2025-02-18 | 2025-02-18 | 2025-02-18 |  |  |  | 2025-03-05 | 2025-03-10 | 2025-03-10 |  |  | N/A | N/A | N/A | 43785 | 43785 |  | 39234.98 | 39234.98 |  |  | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-02-18 | 2025-02-18 | N/A | Ongoing Procurement Process
310300100001000 | MATERIALS & TOOLS REPAIR & VENTILATION FOR CSS NC II (SHOP/WORKSTATION) | LADY KRISSETTE B. ANDICOY | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  |  |  | 2025-03-26 | 2025-03-31 | 2025-03-31 |  |  | N/A | N/A | N/A | 109570 | 109570 |  | 74658 | 74658 |  |  | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | N/A | Ongoing Procurement Process
310300100001000 | TRAINING CONSUMABLES AND INSTITUTION ASSESSMENT FOR DIPLOMA IN HOSPITALITY MAMAGEMANT AND TECHNOLOHY II MAJOR IN FOOD PRPCESSING NC II (FEBRUARY 25,2025 | JENEBELE T. CONAHAP | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-18 | 2025-04-18 |  | 2025-04-18 | 2025-04-18 | 2025-04-18 |  |  |  | 2025-04-21 | 2025-04-24 | 2025-04-24 |  |  | N/A | N/A | N/A | 37000 | 37000 |  | 25978 | 25978 |  |  | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | N/A | Ongoing Procurement Process
310300100001000 | SUPPLIES AND MATERIALS FOR TWSP MACHINING NC II | RONALDO J. SIASON | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-18 | 2025-04-18 |  | 2025-04-18 | 2025-04-18 | 2025-04-18 |  |  |  | 2025-04-21 | 2025-04-24 | 2025-04-24 |  |  | N/A | N/A | N/A | 195500 | 195500 |  | 133500 | 133500 |  |  | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | N/A | Ongoing Procurement Process
310300100001000 | CONSUMABLES FOR DRESSMAKING NC II FOR DGFDT I-A & DGFDT I-B | FAITH G. TARROZA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-03 | 2025-03-03 |  | 2025-03-03 | 2025-03-03 | 2025-03-03 |  |  |  | 2025-03-04 | 2025-03-07 | 2025-03-07 |  |  | N/A | N/A | N/A | 73762 | 73762 |  | 57290 | 57290 |  |  | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | N/A | Ongoing Procurement Process
310300100001000 | TRAINING CONSUMABLES IN COOKERY NC II (DHMT II-A & IIB) | GRETCHEN J. NUBOG | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-21 | 2025-03-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  |  |  | 2025-01-22 | 2025-01-27 | 2025-01-27 |  |  | N/A | N/A | N/A | 241916 | 241916 |  | 210426 | 210426 |  |  | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | N/A | Ongoing Procurement Process
310300100001000 | FIXTURES, SPORTING EQUIPMENT & SUPPLIES FOR WELLNESS PROGRAM OF ZSPI | PRESCO P. CAÑETE | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-24 | 2025-03-24 |  | 2025-03-24 | 2025-03-24 | 2025-03-24 |  |  |  | 2025-03-25 | 2025-03-28 | 2025-03-28 |  |  | N/A | N/A | N/A | 27400 | 27400 |  | 27200 | 27200 |  |  | N/A | N/A | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | N/A | Ongoing Procurement Process
310300100001000 | MATERIALS FOR ELECTRICAL WIRING FOR THE INSTALLATION FAN IN ACP NC II | MAE JANE G. DAGUPAN | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-14 | 2025-04-14 |  | 2025-04-14 | 2025-04-14 | 2025-04-14 |  |  |  | 2025-04-15 | 2025-04-18 | 2025-04-18 |  |  | N/A | N/A | N/A | 6810 | 6810 |  | 3920 | 3920 |  |  | N/A | N/A | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | N/A | Ongoing Procurement Process
310300100001000 | MATERIALS FOR EARTH MONTH POSTER MAKING CONTEST | JOHN MICHAEL L. MONTILLANO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-25 | 25/4/25 |  | 2025-04-25 | 2025-04-25 | 2025-04-25 |  |  |  | 2025-04-25 | 2025-04-28 | 2025-04-28 |  |  | N/A | N/A | N/A | 6000 | 6000 |  | 1900 | 1900 |  |  | N/A | N/A | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | N/A | Ongoing Procurement Process
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES FOR HOUSEKEEPING NC II (SHS TVL LEARNERS - 200/2ND BATCH | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-04-28 | 2025-04-28 |  | 2025-04-28 | 2025-04-28 | 2025-04-28 |  |  |  | 2025-04-29 | 2025-03-28 | 2025-03-28 |  |  | N/A | N/A | N/A | 67000 | 67000 |  | 57700 | 57700 |  |  | N/A | N/A | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | N/A | Ongoing Procurement Process
310300100001000 | CONSUMABLES FOR DRESSMAKING NC II FOR DGFDT I-A & DGFDT I-B | FAITH G. TARROZA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-03-03 | 2025-03-03 |  | 2025-03-03 | 2025-03-03 | 2025-03-03 |  |  |  | 2025-03-04 | 2025-03-07 | 2025-03-07 |  |  | N/A | N/A | N/A | 7360 | 7360 |  | 5600 | 5600 |  |  | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | N/A | Ongoing Procurement Process
310300100001000 | [32 empty] | N/A | N/A
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTRATION ON ONE STOP SHOP SERVICES (LEMON GRASS JUICE MAKING) | REYNA JANE TAPIAN | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2025-02-14 | 2025-02-14 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 | 0 | 0 |  | 2025-02-17 | 2025-02-14 | 2025-02-14 | -3 |  | N/A | N/A | N/A | 3700 | 3700 |  | 3674 | 3674 |  | 0.007027 | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | N/A | Ongoing Procurement Process
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 1069277 | 1069277 | 0 | 829179.98 | 829179.98 | 0 | 36.31%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | Approved:
|  | LYNDRE G. BAYOTAS | [7 empty] | ANALYN J. ELLIORIN, Ed.D | [18 empty] | GLADYS A. TIONGCO, Ed.D.
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 4187833.98
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 45
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1.1163 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.087 | 0.27907 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 1 | 1 | 2000 | 1960 | 100% | 98% | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 2 | 0 | 0 | 0 | 0% |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 43 | 43 | 4044512.36 | 3288873.98 | 100% | 81.32% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 1 | 1 | 907600 | 897000 | 100% | 98.83% | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 47 | 45 | 4954112.36 | 4954112.36 | 75% | 92.72% | 0 | 0
Total for Alternative Mode of Procurement | 47 | 45 | 4954112.36 | 4187833.98 | 75% | 92.72% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 27 | 57.45% | 3983947.76 | 78.84% | 3454892.3 | 80.65% | 0.1328
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 20 | 42.55% | 1069277 | 21.16% | 829179.98 | 19.35% | 0.22454
Total | 47 | 100% | 5053224.76 | 100% | 4284072.28 | 100% | 0.15221
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 47 | 5053224.76
Total | 47 | 5053224.76
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell